## Tasks
Task ID | Sprint | Task | Estimate (S/M/L) | Depends On | Priority | Status | Owner | PR Link | Requirement IDs | Test Case IDs
T-001 | Sprint 1 | Setup canonical repository layout | M |  | P0 | Not Started
T-002 | Sprint 1 | Configure Python packaging and environment management | S | T-001 | P0 | Not Started
T-003 | Sprint 1 | Configure CMake build for cpp_core + tests + benchmarks | M | T-001 | P0 | Not Started
T-004 | Sprint 1 | Setup CI matrix (Windows/Linux) with lint/test gates | M | T-002,T-003 | P0 | Not Started
T-005 | Sprint 1 | Implement structured logging (Python + C++) with run_id correlation | M | T-003 | P0 | Not Started
T-006 | Sprint 1 | Implement typed config loader (TOML + env overlay) | S | T-002 | P0 | Not Started
T-007 | Sprint 1 | Implement secrets redaction helpers | S | T-006 | P0 | Not Started
T-008 | Sprint 1 | Create Nanobind module skeleton + version() + sum(array) | M | T-003 | P0 | Not Started
T-009 | Sprint 1 | Add bridge smoke tests (dtype/shape/error mapping) | S | T-008 | P0 | Not Started
T-010 | Sprint 2 | Implement market data loaders (parquet/csv) | M | T-002 | P0 | Not Started
T-011 | Sprint 2 | Implement normalization to market arrays contract | M | T-010 | P0 | Not Started
T-012 | Sprint 2 | Implement data validators (monotonic/duplicates/gaps/spread) | M | T-011 | P0 | Not Started
T-013 | Sprint 2 | Implement data version/hash lineage metadata | S | T-011 | P0 | Not Started
T-014 | Sprint 2 | Implement signal adapters with alignment checks | M | T-011 | P0 | Not Started
T-015 | Sprint 2 | Implement baseline signal generators (EMA, Williams %R) | M | T-014 | P0 | Not Started
T-016 | Sprint 3 | Implement C++ SignalEngine deterministic loop | L | T-008,T-011,T-014 | P0 | Not Started
T-017 | Sprint 3 | Implement entry/exit tie-break policy + docs | S | T-016 | P0 | Not Started
T-018 | Sprint 3 | Implement fill model (spread/slippage) | M | T-016 | P0 | Not Started
T-019 | Sprint 3 | Implement commission/swap hooks | S | T-018 | P1 | Not Started
T-020 | Sprint 3 | Implement portfolio accounting (balance/equity/pnl/margin) | L | T-016 | P0 | Not Started
T-021 | Sprint 3 | Implement outputs: trades, equity, metrics baseline | M | T-020 | P0 | Not Started
T-022 | Sprint 3 | Bind run_bars_signals via Nanobind + GIL release | M | T-016,T-008 | P0 | Not Started
T-023 | Sprint 3 | Implement persistence tables (runs/configs/metrics/trades/artifacts) | M | T-013 | P0 | Not Started
T-024 | Sprint 3 | Implement reproducibility bundle writer | S | T-023 | P0 | Not Started
T-025 | Sprint 4 | Implement C++ BatchRunner thread-pool scheduling | L | T-016 | P0 | Not Started
T-026 | Sprint 4 | Implement deterministic per-run seed assignment | S | T-025 | P0 | Not Started
T-027 | Sprint 4 | Implement top-K reduction + leaderboard | M | T-025 | P0 | Not Started
T-028 | Sprint 4 | Implement Python run_batch orchestration | M | T-022,T-025 | P0 | Not Started
T-029 | Sprint 4 | Implement WFO orchestration scaffold | M | T-028 | P1 | Not Started
T-030 | Sprint 4 | Implement optimization_jobs/results persistence | S | T-023,T-028 | P0 | Not Started
T-031 | Sprint 4 | Add perf benchmarks (single/batch/bridge overhead) | M | T-025,T-022 | P0 | Not Started
T-032 | Sprint 5 | Implement EventEngine event queue + dispatch | L | T-016 | P1 | Not Started
T-033 | Sprint 5 | Implement pending orders lifecycle (limit/stop) | M | T-032 | P1 | Not Started
T-034 | Sprint 5 | Implement modify/cancel + partial close | M | T-033 | P1 | Not Started
T-035 | Sprint 5 | Implement intrabar SL/TP policy options | M | T-033 | P1 | Not Started
T-036 | Sprint 5 | Ensure signal/event output schema parity | S | T-032,T-021 | P1 | Not Started
T-037 | Sprint 5 | Add mode comparison diagnostics | S | T-036 | P1 | Not Started
T-038 | Sprint 6 | Implement RiskGovernor hard limits + exposure checks | M | T-020 | P0 | Not Started
T-039 | Sprint 6 | Implement circuit breaker + kill switch | S | T-038 | P0 | Not Started
T-040 | Sprint 6 | Implement MT5 ZeroMQ protocol contracts | L | T-006 | P0 | Not Started
T-041 | Sprint 6 | Implement gateway reconnect + heartbeat | M | T-040 | P0 | Not Started
T-042 | Sprint 6 | Implement startup reconciliation (positions/orders/account) | M | T-041 | P0 | Not Started
T-043 | Sprint 6 | Implement fail-safe halt on ambiguity/disconnect | S | T-042,T-039 | P0 | Not Started
T-044 | Sprint 6 | Implement paper mode parity engine + realism profiles | M | T-022 | P1 | Not Started
T-045 | Sprint 7 | Implement REST endpoints for runs and optimize | M | T-023 | P1 | Not Started
T-046 | Sprint 7 | Implement WebSocket streaming for run updates | S | T-045 | P1 | Not Started
T-047 | Sprint 7 | Implement API auth/token guard | S | T-045 | P1 | Not Started
T-048 | Sprint 7 | Implement PySide6 run launcher + charts + blotter | L | T-023 | P1 | Not Started
T-049 | Sprint 7 | Implement optimization leaderboard UI view | M | T-048 | P1 | Not Started
T-050 | Sprint 7 | Implement reporting pipeline (md/html + repro footer) | M | T-021,T-024 | P1 | Not Started
T-051 | Sprint 8 | Implement WAL journaling and replay routines | L | T-023 | P0 | Not Started
T-052 | Sprint 8 | Implement crash recovery + stale lock cleanup | M | T-051 | P0 | Not Started
T-053 | Sprint 8 | Implement security hardening checklist in CI | S | T-007,T-004 | P1 | Not Started
T-054 | Sprint 8 | Implement observability metrics export + dashboards | M | T-005 | P1 | Not Started
T-055 | Sprint 8 | Define SLOs and alert thresholds + runbook | S | T-054 | P1 | Not Started
T-056 | Sprint 8 | Final closure: P0 gap audit + sign-off package | M | T-001..T-055 | P0 | Not Started
T-057 | Sprint 6 | Implement idempotent order keys for live order submission | M | T-040 | P0 | Not Started
T-058 | Sprint 6 | Implement reconnect retry deduplication window | M | T-041,T-057 | P0 | Not Started
T-059 | Sprint 6 | Implement clock-sync guard and drift thresholds | S | T-041 | P0 | Not Started
T-060 | Sprint 6 | Implement broker rules snapshot cache (min lot/step/stops/sessions) | M | T-040 | P0 | Not Started
T-061 | Sprint 6 | Implement daily reconciliation report (local vs broker diffs) | M | T-042 | P0 | Not Started
T-062 | Sprint 6 | Implement manual kill-switch command channel | S | T-039,T-040 | P0 | Not Started
T-063 | Sprint 6 | Implement latency telemetry (signal->send->ack/fill) + percentile metrics | M | T-040,T-054 | P1 | Not Started
T-064 | Sprint 6 | Implement degraded-mode guards (stale quotes/spread blowout/auto-halt) | M | T-038,T-043 | P0 | Not Started